Design Collaboration Implementation Form (DCIF) for the Design Office activities related to the EC HV Power Supply PA

5.2.P4.IN.01

Abstract

This document complements the Procurement Arrangement (PA) documentation by focussing on IO DO & DA DO collaboration organisation, responsibilities, processes & inputs/outputs for the EC HV Power Supply.

.

Major Changes

| Version | Date | Location | What |
| --- | --- | --- | --- |
| 1.0 | 13/04/2011 | - | First in work version |
| 1.1 | 19/09/2013 |  | SEE Cabling Manager is not the software used for the cable tray anymore, it is KCMS. SSD platform is accessible through Windows Remote Application. Deletion of the tender phase in the collaborative workplan. I-Run may not needed. |

Contents

1	Objectives of the DCIF	3

2	Collaboration Scheme	3

2.1	CAD data	3

2.1.1	Choice and justification	3

2.1.2	Evolution of collaboration schemes along the task	3

2.1.3	Acceptance of Multi-CAD design between the DA and its suppliers	3

Diagram data	4

3	Enablers related to this PA	4

3.1	Software	4

3.1.1	For CAD data	4

3.1.2	For diagram data	4

3.1.3	For Piping isometric drawing generation	5

3.2	Standards and templates	5

3.3	Procedures & Documentation	5

3.3.1	For CAD data production	5

3.3.2	For CADENAS use	5

3.3.3	For Diagrams production	5

3.3.4	For Equipment & System (E&S) production	6

3.3.5	For piping isometric drawing production	6

4	Design Offices responsibilities	7

4.1	IO DO responsibilities	7

4.2	DA DO responsibilities	8

5	DO Inputs/Outputs	9

5.1	PA inputs	9

5.2	PA outputs	9

6	Collaborative Workplan	10

7	Contact Persons	14

8	CAD Manual sections applicable for this task	14

9	Design data records	14

10	Glossary	15

# Objectives of the DCIF

This document:

- Is related to the EC HV Power Supply Procurement Arrangement (PA) which includes the design, analysis, qualification, manufacturing, factory testing, delivery, integration, installation and acceptance testing at the ITER Site of the EC HV Power Supply based on a Functional Specification

- Recommends a Collaboration scheme between IO Design Office (DO) and DA Design Office (DO) and characterises the related organisation aspects to be applied for the Procurement Arrangement

- Proposes an implementation plan for the activities of the IO DO and DA DO.

- This document is consistent with the ITER CAD Manual (249WLQ) and the Protocol of Collaboration (24P2F6) between IO DO and DA DO

- Has been written based on the following draft PA documents:

- 5.2.P4.IN.01 EC HV Power Supply main PA (AU2BZA v1.1)

- 5.2.P4.IN.01.1 EC HV Power Supply Annex A (AU3JAT v1.0)

- EC HVPS PA 52.P4.IN.01 Annex B (9C3H4F v1.3)

Note: The present DCIF will be only revised when impacting changes have been identified by IODO within updates of the above documents. Without impact, the present DCIF version remains applicable, the impact analysis of later versions of these documents being acknowledged in the comment field of IDM.

# Collaboration Scheme

## CAD data

### Choice and justification

Synchronous Collaboration Scheme amongst the three possible collaboration schemes (synchronous, asynchronous and scheduled) promoted by IO. It means that IN DA and his supplier will work in direct remote connection in IO Data Base.

Further explanations are available in the Collaboration schemes description (2WS83V)

Justification:

- Functional Specification PA

- Interfaces to be finalised between several procurement packages.

- Several domestic agencies involved on interfacing procured packages.

### Evolution of collaboration schemes along the task

YES        It is anticipated that the DA will develop design data using the synchronous collaboration scheme throughout the final design phase.  If the DA chooses to involve suppliers in some design for manufacturing tasks, the output of those tasks may be managed using a scheduled collaboration scheme.

### Acceptance of Multi-CAD design between the DA and its suppliers

NO

Justification: Because a Synchronous Collaboration Scheme has been promoted.

## Diagram data

Direct Remote Connection promoted by IO.

Justification:

- The EC HV Power Supply use network elements. Their representations (one line and cabling diagrams, PFD and P&ID (fluids diagrams), CODAC…) will be done through a remote connection to the IGE+XAO SEE System Design licenses and its database which is the only reference solution on ITER collaboration diagrams.

- This solution for diagrams:

- Embeds an object-centric DB management of equipments, line and circuits. (IGE+XAO).

- Enables the construction of links between the diagram representation of equipments, lines and circuits with their 3D description within the PDM.

# Enablers related to this PA

## Software

### For CAD data

- IO DO, DA DO and its supplier shall use the CATIA version indicated in the latest version of the ITER CAD Manual released by IO DO, CATIA V5 (R20 SP5 currently). Further changes of CATIA release will be announced officially through the CAD working group and by mail to the DA DO.

- Product Data Management (PDM) system: ENOVIA V5 for IO and DA, and for DA supplier also during the synchronous collaboration phase.

- CATIA V5 E&S workbenches

- Mechanical Standard part management tool (including extensive standard and commercial catalogues which connect to CATIA and ENOVIA): CADENAS software

- CAD Quality checking: Q-checker.

- CATIA customization provided by IO:

- Bill of Material (BOM) (How_to_Generate_VPMNav_BOM_Report (35PZ5Z v1.3) )

- Design Log Book (How to use design logbook (3QFDA9 v1.2) )

For details about IO DO CAD systems, refer to:

ITER CAD Manual Section 1.3 - IO CAD System (249WLQ)

For details of CATIA release, refer to:

ITER CAD Manual Section 7 – CAD Fact Sheet (249WUL)

The DA shall create a direct Remote connection with his contractor, with the support of the IO IT: Solution description: Remote CAD design solution (3VY6HV v1.3)

### For diagram data

The DA DO shall use:

- Engineering Design Diagram System: IGE+XAO SEE System Design (SSD).

- Publication system for all diagrams: ICP.

- For the procurement of Cubicle detailed wiring diagrams, DA shall use IGE+XAO SEE Electrical Expert and have their own licence.

- For the procurement of Cabling diagrams and cabling information, DA shall use IGE+XAO SEE System Design (SSD).

The IO DO will provide:

- A remote access to the IGE+XAO SEE System Design platform via a Windows Remote Application connection with appropriate licences.

- IDM accounts (for ICP access).

For detail about these tools, refer to: Introduction to ITER official Schematic tools (4H3FEP)

### For Piping isometric drawing generation

If isometric drawings have to be produce, the DA DO shall use:

- Isometric system: I-RUN or upper version from Intergraph (previously called ISOGEN) – version 2012 R1 used in IO at the time of the DCIF edition

- Storage of drawings as CATIA Drawing in ENOVIA V5.

## Standards and templates

The DA DO shall use the following ITER standards and templates:

- Diagrams templates and symbols as well related Equipment & System (E&S) setup for SEE-System Design will be enabled for the DA thanks to the configuration of machines.

- During the Synchronous phase, CAT settings recommended by IO and CATIA automation tools related to ITER customisation, including generation of Drawings frames and Titleblocks, will be enabled for the DA and suppliers thanks to the configuration of Teradici machines.

- For the use by the supplier during the scheduled phase, ISO drawing standards are given in the CAD Manual 10 - ISO Drawing Standards (24MZWV v3.0)

## Procedures & Documentation

The DA and IO shall comply with the World wide support concept and procedures (34VB64 v1.0)

### For CAD data production

The DA DO shall comply with IO drawings and models management, approval processes and procedures:

- Procedure for the Management of CAD Work & CAD Data (Models and Drawings) (2DWU2M v1.7)

- Procedure for the Approval of CAD data - CMM , 3D Models & Drawings (2E3UCH v1.5)

- Procedure for the Promotion of CAD Data from In-Work to Draft Status (28LVHH v1.7)

- Hyperlinks to the ITER CAD Manual & How To documents (24N3GT)

- HOW TO CHECK THE CONSISTENCY BETWEEN 2D AND 3D (E9EF4T)

### For CADENAS use

The use of Mechanical Standard Parts shall be done through the CADENAS software

The following methodologies and procedures shall be applied:

- CADENAS Standard Parts – Collaboration Processes (342GSU v1.0)

- How To - CADENAS (35ZJ6Y)

- How To - CADENAS For File Based Users (CITRIX) (342DV4)

### For Diagrams production

IO diagram management, approval processes and procedures shall be applied:

- CAD Manual 14 - Diagram Guidelines (35CY6V v2.0)

- ICP SSD PDF Diagram management functional spec (2N2YX2 v1.3)

- SSD Golden Rules (3TQGM4 v1.1)

In addition, see below the repertory for “How To” produce the diagram

- Plant Diagram (2DW78H)

### For Equipment & System (E&S) production

IO populates its catalogues DB with standards references, commercial references or preliminary design references. The documentation of existing part families is stored in Technical Description Sheet (TDS) (27YG5M) describing the equipment (material, size, attributes…) which are stored on IDM (IDM account needed) under the following link: Catia Plant Designer Catalog Documentation (283AMM).

The 3D representations are stored in ENOVIA and are available by CATIA through the following workbenches:

- Equipment & System \ Multi-discipline

- Equipment & System \ HVAC discipline

- Equipment & System \ Piping discipline

- Equipment & System \ Structure discipline

- Equipment & System \ Preliminary Layout

- Equipment & System \ Electrical Cabling Discipline

For further details on modules to be used depending on the kind of work to perform, you can consult 03 EnS Add-on Documentation (2Y78NL) on §8 “Licensing”.

Designers will have to follow E&S methodologies and ‘’HOW TO’’ stored under: Equipment&System (29FSLN)

### For piping isometric drawing production

The DA shall comply with the following IO requirements:

- Documentation for installation: see §12 of ITER Equipment and Systems Add-On Deployment and Usage (2Y78NL).

- Documentation for production: see How to use ITER Piping ISOmetrics (2W547R).

# Design Offices responsibilities

## IO DO responsibilities

For generic information concerning IO DO responsibility refer to:

ITER CAD Manual 03 - DO Organization and Responsibilities (249WQN)

- To support the DA to create TERADICI connection between selected contractor premises and the CAD workstations hosted at IO site.

- To allow a remote access to the IGE+XAO SEE System Design licences and to the IO Database (via Windows Remote Application) for Verification of E&S data with regards to the Diagrams

- To check on DA designers (or supplier’s) certification from IO.

- To provide IDM accounts to DA DO members and DA supplier DO members to access the reference documents.

- To attribute relevant roles to the DA DOCC and designers (or supplier) in the ITER ENOVIA P&O concept after certification.

- To provide the 2D/3D checker tool.

- To provide Q-Checker profiles

- To support the DA in establishing all customization, setups and settings (Generic CAD supplier package, E&S supplier package…)

- To temporary allow a remote access to the ITER CADENAS Mechanical Standards Parts (via CITRIX) until DA get the CADENAS software licences.

- To support DA with level 3 support as described in World wide support concept and procedures (34VB64 v1.3)

- To provide the inputs identified in §5.1

- To manage the diagram data approval process.

- To inform DA DO about any interface change by using the ENOVIA subscriptions and the corresponding DET process, following the relevant change control process.

- To take in charge the implementation of new catalog parts designed by the DA DO (or its supplier) according to methodologies stated in §3.3.4

- To provide the requested support to the IO RO, IO DI, and other design reviewers, in assessing the functional and integration aspects:

  - For review of the preliminary design from the DA and the suppliers

  - For review of the final design from the DA and the suppliers

  - For the Manufacturing Readiness Review

  - For the acceptance of the ‘As-built’ documentation

## DA DO responsibilities

For generic information concerning DA DO responsibility refer to:

ITER CAD Manual 03 - DO Organization and Responsibilities (249WQN)

- To support their own designers (or supplier’s designers) as described in the  World wide support concept and procedures (34VB64 v1.0):

  - In obtaining the suitable CATIA/ENOVIA training and certifications (if needed), as well as for any other necessary trainings (E&S, SSD, …)

  - In following the proper design methodologies (for the levels 1 and 2)

- To purchase the CADENAS Software licences.

- To purchase Q-Checker licenses (if DA needs more than the number provided by IO (1 at the moment))

- To purchase I-RUN if isometric drawings have to be produce.

- To support the creation of the TERADICI connection within the selected contractor premises to the workstations hosted in IO if it is the DA’s choice

- To provide the outputs identified in §5.2

- To provide the IO DO with the 3D geometry relevant for:

  - The configuration control checking by the IO DI

  - The design checking by the IO RO and the IO DO

- To insure the consistency between 2D definition and 3D geometry delivered to IO

- To insure the consistency of 3D representations delivered to IO (E&S data) with the diagrams provided as PA inputs: Task assisted by the use of a 2D/3D checker utility as provided by IO to detect the most obvious mistakes.

- To put in place the proper procedures to insure that the data passed to IO DO are compliant with the CAD Manual (with a special care of the sections given in §8 of this DCIF).

- To promote all CAD data to DA-Draft under ENOVIA for all deliverables (intermediate and final).

- To align the PA design with the updated environment and context once IODO has informed about any interface modification through the DET following the appropriate change management process. The access to the context of design is enabled by his constant connection to the ITER Digital Mock-up (Enovia).

- To follow the temporary procedure which allows a remote access to the IO’s CADENAS Mechanical Standards Parts (via CITRIX) until they purchase the proper CADENAS licences.

- To take in charge 3D models creation for new catalog parts according to methodologies stated in §3.3.4

# DO Inputs/Outputs

## PA inputs

- 2D Drawings, 3D Models in Conceptual Design (CD) maturity, and in approved status.

- Configuration Management Models (CMM) of the system for EC HV Power Supply. (ITER_D_2UXHNM)

## PA outputs

- The DA shall provide the IO DO with the 3D models  and 2D drawings , at each PA review according to the definition given in the latest approved version of the Design Review Procedure (2832CF)

    - Preliminary design for the Preliminary Design Review

    - Final Design for the Final Design Review

    - Manufacturing Design as input of Manufacturing Readiness Review

    - As-Built Design

    - As-Installed design

The DA or its supplier should use and version the models and drawings transferred by IO through the Design Data DET. The creation of new model references is limited to the case of parts added to the EC HV Power Supply assembly because not existing in the initial design provided by IO.

- This data produced by the DA or its supplier directly in ITER ENOVIA DB shall  be promoted into DA-Draft status:

    - On a regular basis for checking and monitoring by IO (Frequency to be defined in preparation phase, according to the detailed work plan provided by DA)

    - In relation with any Project change request (PCR) or deviation change request (DCR)

    - Before manufacturing documents are checked for manufacturing agreement

    - As Built models and drawings at the end of the manufacturing phase

- In addition, the DA shall provide:

    - Design Log Book (File attached like document in ENOVIA / CATIA customisation provided by IO DO-) will be filled in order to allow the tracking of design changes and the related CAD data versioning.

    - Bill Of Material (CATIA customisation provided by IO DO)

    - CAD Quality Checking verifying the compliance of the CAD models with the CAD Manual

These documents are provided within the DET process run by the DA to perform any delivery of CAD data.

# Collaborative Workplan

Identification here after of the logical sequences of IO’s and DA’s DO actions, related to the expected outputs per phase.

| PREPARATION PHASE |  |
| --- | --- |
| DA DO | - To submit the DA workplan. - To inform IO DO about the identified DA/CDO actors and corresponding roles. |
| IO DO | - To check and approve the DA workplan, adaptation or merge of the present DO Collaborative workplan if needed. |
| DA DO | - To purchase the CADENAS Software licences. - To purchase Q-Checker licenses (if DA needs more than the number provided by IO (2 at the moment)) - To purchase IGE+XAO SEE Electrical Expert licences - To purchase IGE+XAO SEE Cabling Manager licences - To purchase I-RUN - To create the direct remote connection within the selected contractor’s premises - To put in place the proper procedures to insure that the data passed to IO DO are compliant with the CAD Manual (with a special care of the sections given in §8 of this DCIF). |
| IO DO | - To identify the CAD data (2D/3D) representing an interface with the system sub-assemblies - Definition of the environment by room filtering - Listing of interfaces. - To identify the diagram data. - To adapt, if needed, the 3D CAD data structure granularity. - To create IDM account (if needed) - To provide the 2D/3D checker tool. - To provide Q-Checker profiles - To allow a remote access to the IGE+XAO See System Design licences and to the IO Database (via CITRIX) - To assist the DA DO in creating the direct remote connection with selected contractor premises - To temporary allow a remote access to the ITER CADENAS Mechanical Standards Parts (via CITRIX) until DA purchase CADENAS software. - To support DA with level 3 support as described in World wide support concept and procedures - To enable the DA all customization, setups and settings (Generic CAD supplier package, E&S supplier package…) |

| PREPARATION PHASE - CONTINUED |  |
| --- | --- |
| DA DO | - To support their own designers (or supplier) as described in the World wide support concept and procedures: - In obtaining the suitable CATIA/ENOVIA training and certifications (if needed), as well as for any other necessary trainings (E&S, SSD, …) - In following the proper design methodologies (for the levels 1 and 2) |
| IO DO | - To check on DA (or supplier) designer certifications. - To attribute relevant roles to the DA DOCC and designers (or supplier) in the ITER ENOVIA P&O concept after certification. - To transfer the data ownership |

| PA PHASE I: TENDERING DESIGN AND FINAL DESIGN |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- |
| Tendering design phase |  |  |  |  |  |  |
| DA DO |  |  |  | - Production of Call For Tender (CFT) drawings and documentation. - Export of CFT drawings to IO DO, and related 3D data (DET process). |  |  |
| IO DO |  |  |  | - Checks CFT drawings, and related 3D geometry data against IO’s: - Configuration Models Management (CMM). - Interfaces models and drawings. - Reports to IO RO and IO DI the conformance of CFT data with CMM. - If agreement with IO RO and IO DI, storage and registration of the CFT drawings and related 3D data into the IO CAD DB. - If new CAD references have been generated in the ENOVIA CFT design registration, then export of the updated references to the DA to take into account new references numbers (DET). |  |  |
| DA DO |  |  |  | - Export of CFT CAD data to suppliers. |  |  |
| FINAL DESIGN Phase |  |  |  |  |  |  |
| MAIN EXECUTION STEPS |  |  |  |  |  |  |
| Direct Remote connection (for Diagram data) |  |  |  |  |  |  |
| DA DO CDO |  |  |  |  | - To perform diagrams once connected to the ITER SSD DB via CITRIX. - DA is responsible of the continuous identification of data representing an interface between the system and others. The maintenance of the design context is DA’s responsibility and is enabled by its constant connection to the ITER database via CITRIX. - To publish the diagrams under ICP. |  |
| IO DO |  |  |  |  | - IO DO supports DA and its supplier designers on ITER DIAGRAMS and CITRIX methodologies. - IO DECO monitors the compliance of DIAGRAMS data, with the ITER design rules. |  |
| FINAL DESIGN Phase - CONTINUED |  |  |  |  |  |  |
| Synchronous scheme (for CAD data) |  |  |  |  |  |  |
| CDO DA DO |  |  | - To perform Final Design once connected to the ITER ENOVIA DB, - To follow the temporary procedure which allows a remote access to the ITER CADENAS Mechanical Standards Parts (via CITRIX) until they purchase the proper CADENAS licences. - Isometric data performed by designers based on their 3D representations thanks to I-RUN and saved under ENOVIA DB. - DA designers are responsible of the continuous identification of CAD data representing an Interface with the environment. The maintenance of the context of design is DA responsibility and is enabled by his constant connection to the ITER Digital Mock-up (Enovia). |  |  |  |
| IO DO |  |  | - To create/update Configuration Management Models (CMM) for the objects interfacing with DAs works, when relevant. - To inform DA DO about any interface change by using the ENOVIA subscriptions and the corresponding mail or meetings if required. - To monitor the compliance of 3D and 2D CAD models with the ITER CAD Manual rules. |  |  |  |
| INTERMEDIATE DELIVERIES (every month) |  |  |  |  |  |  |
| CDO |  | - To stop designing until the DA draft promotion is achieved. |  |  |  |  |
| DA DO |  | - To check on CAD quality issues. - To insure the consistency between 2D drawings and 3D models delivered to IO at any PA stage. - To insure the consistency between diagrams and 3D models delivered to IO at any PA stage (task assisted by the use of a 2D/3D checker utility to detect the most obvious mistakes). - To promote to DA Draft the data. - To send to IO DO the DET mentioning DA Draft promotion is done, with associated BOM. |  |  |  |  |
| IO DO |  | - To monitor the compliance of 3D CAD models and 2D drawings of the detailed designs with the ITER CAD Manual rules. IO DECO provides the requested support to the IO RO and IO DI, and other design reviewers, in assessing the functional and integration aspects. - To Draft the data depending upon the agreement of IO DI and IO RO. - To send back to DA DO the DET mentioning Draft promotion is done. |  |  |  |  |
| FINAL DESIGN REVIEW |  |  |  |  |  |  |
| DA DO IO DO |  | - Final Design Review: Identical sequence and involvement of IO DO and DA DO as shown intermediate deliveries above, apart the following: - Data to be finally approved through the Final Design Review is transmitted to IO at least 4 weeks before - Design Review involves (in addition of the design reviewers identified in regular design reviews) all IO ROs of interfacing components - Promotion to ‘Approved’ status of the CAD data delivered by the DA DO performed by the IO DECO in ITER DMU |  |  |  |  |
| PA PHASE II: MANUFACTURING AND DELIVERY PHASE |  |  |  |  |  |  |
| DA shall produce the Manufacturing Design according to the phase above and eventual updates during the manufacturing. |  |  |  |  |  |  |
| MANUFACTURING READINESS REVIEW |  |  |  |  |  |  |
| DA DO IO DO |  |  | - Manufacturing Readiness Review: Identical sequence and involvement of IO DO and DA DO as shown intermediate deliveries above, apart the following: - Data to be finally approved through the Manufacturing Readiness Review is transmitted to IO at least 4 weeks before - Design Review involves (in addition of the Design reviewers identified in regular design reviews) all IO ROs of interfacing components - Promotion to ‘Approved’ status of the CAD data delivered by the DA DO performed by the IO DECO in ITER DMU |  |  |  |
| AS-BUILT READINESS REVIEW |  |  |  |  |  |  |
| DA DO IO DO | - As Built Readiness Review: Identical sequence and involvement of IO DO and DA DO as shown intermediate deliveries above, apart the following: - Data to be finally approved through the As-Built Readiness Review is transmitted to IO at least 4 weeks before - Design review involves (in addition of the design reviewers identified in regular design reviews) all IO ROs of interfacing components. - Promotion to ‘Approved’ status of the CAD data delivered by the DA DO performed by the IO DECO in ITER DMU. |  |  |  |  |  |

| PA Phase III: INSTALLATION AND FINAL ACCEPTANCE TESTS PHASE |  |
| --- | --- |
| DA shall produce the As Installed Design according to components, buildings and interfaces updates delivered by IO |  |
| AS-INSTALLED READINESS REVIEW |  |
| DA DO IO DO | - As Installed Readiness Review: Identical sequence and involvement of IO DO and DA DO as shown intermediate deliveries above, apart the following: - Data to be finally approved through the As- Installed Readiness Review is transmitted to IO at least 4 weeks - Design review involves (in addition of the design reviewers identified in regular design reviews) all IO ROs of interfacing components. - Promotion to ‘Approved’ status of the CAD data delivered by the DA DO performed by the IO DECO in ITER DMU. |
| DA DO | - To transfer back to IO the data ownership. |

# Contact Persons

The IO TRO; IO RO are named in this PA.

For IO DO related issues, the following persons are involved:

| IO DOCC | Eric Thomas |
| --- | --- |
| IO monitor | TBD during KOM |
| IO DECO | Barry Beckett |
| IO E&S Catalog Coordinator | Frederic Autogue |
| IO DO Plant Design Section Leader | Giuliano Dalle Carbonare |
| IO DO Configuration Control Section Leader | Heinz Heidl |
| IO DO Head | Eric Martin |

For DA DO related issues, the following persons are involved:

| DA DOCC | Shrishail Padasalagi |
| --- | --- |
| DA DECO | TBD at the start of the PA |

At the start of the phase I, the DA will nominate a Design Coordinator (DECO) amongst the visiting DA designers. His role, in addition of normal CAD design actions, will be to supervise and monitor the design activities performed by the other designers, and to perform operations related to data lifecycle management (promotion to draft, interfaces list maintenance,…). Clarification of this role will be discussed during kick-off meeting.

IO DO Monitor: Monitors the roll-out of Collaborative tasks (Design Collaboration Implementation Monitoring Process).

# CAD Manual sections applicable for this task

The requirements and recommended methodologies given in the ITER CAD Manual are to be followed for this design task. See the following hyperlinks for the list of the ITER CAD manual sections & how to documentation:

    - Hyperlinks to CAD Manual - Training Docs - How To - Catalogs - What Is - AVI (24N3GT)

The ITER CAD manual covers a wide range of design activity types. After submission of the DA DO detailed workplan to IO, the IO DO will define which detailed methodologies from the CAD Manual should be applied, in particular when the CAD Manual includes several options.

# Design data records

DO data and changes are followed up through several documents:

  - BOM

  - DET (for data ownership)

  - Design Log Book

  - Programme reports (reviews, approvals…)

Certain of those documents will be recorded through the Design Collaboration Implementation Monitoring for a more efficient follow-up of the DO activities related to the EC HV Power Supply PA.

# Glossary

The report of the ITER abbreviations database is available on IDM and in this linked document: ITER Abbreviations (2MU6W5)

| Abbreviation | Real Name/Definition |
| --- | --- |
| AB | As Built |
| BOM | Bill Of Material |
| CAD | Computer Aided Design |
| CD | Conceptual Design |
| CDO | Contractor Design Office |
| CITRIX | Solution enabling a distant connection to the ITER DMU – not requiring any specific resource or machine |
| CMM | Configuration Management Models |
| DA | Domestic Agency |
| DB | Data Base |
| DCIF | Design Collaboration Implementation Form |
| DCIM | Design Collaboration Implementation Monitoring |
| DCR | Design Change Request |
| DDD | Design Description Document |
| DECO | Design Coordinator |
| DER | Data Exchange Request |
| DET | Data Exchange Transfer |
| DI | Design Integration |
| DMU | Digital Mock-Up |
| DO | Design Office |
| DOCC | Design Office Collaboration Coordinator |
| EC | Electron Cyclotron |
| ENOVIA | PDM used in ITER. Database where all ITER CAD data is stored and made accessible to ITER contributors. |
| E&S | Equipment and System |
| FD | Final Design |
| HD | Hard Drive |
| HV | High Voltage |
| IDM | ITER Document Management |
| IO | ITER Organization |
| IT | Information Technology |
| KOM | Kick-Off Meeting |
| MD | Manufacturing Design |
| PD | Preliminary Design |
| PDM | Product Data Management |
| P&O | People & Organisation |
| RO | Responsible Officer |
| QA | Quality Assurance |
| TBD | To Be Defined |
| TRO | Technical Responsible Officer |
| VPN | Virtual Private Network |