**Annex III b– PRICE SCHEDULE**

**Contract: Detailed thermal and structural design of 6 Diagnostic First Walls**

**Reference: IO/21/CFE/10022610/CPT**

All prices shall be in Euros (€) net of all duties and taxes. As an international organisation the ITER Organization is exempt from all taxes and duties. Applicable taxes (if any) shall be shown separately. The Financial Offer shall be submitted in the basis of the following:

Having examined all the Documents attached to this Request for Quotation, including the Technical Specification for the performance of theServices, and having examined all conditions and factors which might in any way affect the cost or time of performance thereof, we the undersigned, offer to complete the Services upon the terms and conditions set forth in the Proposal Documents for the following price

|  |  |  |  |
| --- | --- | --- | --- |
| D# | Deliverable description as defined in section 7 in Technical Specifications ref ITER\_D\_ 6CVFRN v1.1) | Due date | Amount in EUR |
| D01 | Cooling design (CAD models) and Supporting analyses results justifying the performance of 3 first DFWs in Equatorial PP#17. | T0\* + 3 months | *to be added* |
| D02 | Structural integrity justification including cyclic elastoplastic ratcheting analysis of 3 first DFWs in Equatorial PP#17 | T0 + 6 months | *to be added* |
| D03 | Cooling design (CAD models) and Supporting analyses results justifying the performance of 3 last DFWs in Equatorial PP#17 and upper PP#2. | T0 + 9 months | *to be added* |
| D04 | Structural integrity justification including cyclic elastoplastic ratcheting analysis of 3 last DFWs in Equatorial PP#17 and upper PP#2 | T0 + 12 months | *to be added* |
|  | **Total** |  | ***to be added*** |

\**T0: Kick off Meeting date, to take place within a month after the signature of the contract by both parties*

The proposed milestone payment plan is as follows:

|  |  |  |  |
| --- | --- | --- | --- |
| M# | Details | Due date | Amount in EUR |
| M1 | Successful completion of D01 | T0\*+ 4 months | *to be added* |
| M2 | Successful completion of D02 | T0+ 7 months | *to be added* |
| M3 | Successful completion of D03 | T0+ 10 months | *to be added* |
| M4 | Successful completion of D04 | T0+ 13 months | *to be added* |
| ***Total*** | | | ***to be added*** |

*\*T0: Kick off Meeting date, to take place within a month after the signature of the contract by both parties*

|  |  |  |
| --- | --- | --- |
| Signature: |  | COMPANY STAMP |
| Name: |  |
| Position: |  |
| Tel: |  |
| Email: |  |
| Date: |  |