**Annex III b– PRICE SCHEDULE**

**Contract: Specialist work relating to Thomson Scattering Oversight**

**Reference: IO/21/CFE/10020665/CPT**

All prices shall be in Euros (€) net of all duties and taxes. As an international organisation the ITER Organization is exempt from all taxes and duties. Applicable taxes (if any) shall be shown separately. The Financial Offer shall be submitted in the basis of the following:

Having examined all the Documents attached to this Request for Quotation, including the Technical Specification for the performance of theServices, and having examined all conditions and factors which might in any way affect the cost or time of performance thereof, we the undersigned, offer to complete the Services upon the terms and conditions set forth in the Proposal Documents for the following price

|  |  |  |  |
| --- | --- | --- | --- |
| D# | Deliverable summary (extensive description in Technical Specifications ref ITER\_D\_ 4QJCTA v1.0) | Due date | Amount in EUR |
| D01 | 55.C1&C2: progress EWP for supports in the Gallery. | T0\* + 3 months | *to be added* |
| D02 | 55.C2: hold FDR for in-vessel laser Beam Dump | T0+ 4 months | *to be added* |
| D03 | 55.C2: Analysis of the needed modifications following on the third shutter prototype tests. | T0+ 6 months | *to be added* |
| D04 | 55.C2: Analysis of the data collected by JA-DA for dual laser spectral calibration. | T0+ 7 months | *to be added* |
| D05 | 55.C2: Support for the final development of beam alignment method and assessment of the performances. | T0+ 8 months | *to be added* |
| D06 | 55.C2: Closure of cat-1 chits of Beam Dump FDR and cat-2 closure proposal. | T0+ 10 months | *to be added* |
| D07 | 55.C1: Support to EUDA and their contractors for design of CPTS. | T0+ 12 months | *to be added* |
| D08 | Contract summary report. | T0+ 12 months | *to be added* |
|  | **Total** |  | ***to be added*** |

\**T0: Date when Contract is signed by both parties*

The proposed milestone payment plan is as follows:

|  |  |  |  |
| --- | --- | --- | --- |
| M# | Details | Due date | Amount in EUR |
| M1 | Successful completion of D01 and D02 | T0\*+ 5 months | *to be added* |
| M2 | Successful completion of D03, D04 and D05 | T0+ 9 months | *to be added* |
| M3 | Successful completion of D06, D07 and D08 | T0+13 months | *to be added* |
| ***Total*** | | | ***to be added*** |

|  |  |  |
| --- | --- | --- |
| Signature: |  | COMPANY STAMP |
| Name: |  |
| Position: |  |
| Tel: |  |
| Email: |  |
| Date: |  |

*\*T0: Date when Contract is signed by both parties*